## September
RIE Unscheduled Care Priorities Workplan
2018-09-01
Performance Trajectory submitted: 91.3%
| September Trajectory | Priority | Lead | Priorities to be addressed | Anticipated Start Date | Timescale | Overall Anticipated Performance Improvement
Flow One | MI improvement in performance to achieve 96% for the month with longer term view of achieving 100%. To achieve this, the following actions need to be addressed;
| 98% | NHS 24 Redirection | GC | Longer term plan to be discussed following Festival trial | 2018-08-01 | 60 days | 0.001%
|  | Demand & Capacity | SB | Daily Flow ANP consistency to be put in place. Now looking at what can be done to improve TC4 patients | 2018-09-01 | 30 days | 0.2%
|  | Dedicated MIU | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 4%
Flow Two | Improve first assessment within majors to 85%. The following actions to achieve this are detailed below;
| 82% | Majors Triage Review | EJ/MW | Aim of reducing each patient's LOS by 10mins was agreed by the team with a lengthy time scale put in place. To identify with team any quick improvement pieces that can be implemented in the interim | 2018-08-01 | 90 days | 7%
|  | Diagnostics Improvement | SE/GC | Staffing to be mapped against activity and identify potential gaps of investment | 2018-08-01 | 60 days | 0.1%
|  | GP Assessment Area | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 5%
|  | Short Stay Observation Unit | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 0.9%
|  | Interface Team | JS/GC | Staffing to be mapped against activity with the aim of expanding to seven days a week | 2018-08-01 | 60 days | Awaiting feedback regarding staffing and how many additional patients can be reviewed
|  | Avoiding admission to main arc | JS/GC | Home First & locality involvement required along with hot clinic expansion to help quanitfy the admission avoidance numbers | 2018-09-01 | 90 days | 0.2%
|  | Ambulatory Care Expansion | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 2%
|  | AMU Workforce Review | JS/GC | AHP, OT/PT, Pharmacy levels to be included | 2018-09-01 | 90 days | 0.2%
|  | Flow Coordinator Role | GC/JW | Role to be reviewed along with escalation policy | 2018-09-01 | 60 days | 2%
Flow Three | Improve medical admission pathways to 85%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identified below;
| 80% | Reducing bed occupancy in the main arc | GC |  | 2018-09-01 | 90 days | 1%
|  | LOS Improvement Board | CM/MP | Follow up meetings with future directorates to be put in diaries | 2018-03-01 | 90 days | 1%
Flow Four | Improve surgical admission pathways to 75%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identifed below;
| 75% | Hot Clinic Access/Ambulatory Care | IG/KT | Team to review all hot clinic pathways and ensure parity across surgical footprint | 2018-08-01 | 60 days | 5%
|  | Specialty Pull | IG/MG/CM | A succint pathway to be put in place across the surgical directorate as a whole so that patients can be admitted earleir in their emergency pathway | 2018-08-01 | 90 days | 2%
Data & Recording | To align our reporting with SG and to allow us to focus and monitor improvement
|  | New suite of reports to track against the Flows | ADR/RP | LAS to meet to discuss future Tableau plans | Ongoing | 60 days | n/a
Adjusted Performance for September | 91.3%

## Week 1 - WC 3rd
RIE Unscheduled Care Priorities Workplan
September Week Beginning 03.09.18
Performance Trajectory submitted: 91.3%
Weekly Performance: 75.3%
| Sept Trajectory | Week's Performance | Priority | Lead | Priorities to be addressed | Anticipated Start Date | Timescales | Overall Anticipated Performance Improvement | Main Issues | Update Progress
Flow One | MI improvement in performance to achieve 96% for the month with longer term view of achieving 100%. To achieve this, the following actions need to be addressed;
| 98% | 88.45% | NHS 24 Redirection | GC | Longer term plan to be discussed following Festival trial | 2018-08-01 | 60 days | 0.001% | Follow up meeting to be held to confirm long term redirection options | Overall reduced performance by 3.17% compared to last week
|  |  | Demand & Capacity | SB | Daily Flow ANP consistency to be put in place. Now looking at what can be done to improve TC4 patients | 2018-09-01 | 30 days | 0.2% | Sue addressing inconsistencies in flow ANP role to ensure arity across shifts
|  |  | Dedicated MIU | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 4% | Paper to be submitted Friday 14th
Flow Two | Improve first assessment within majors to 85%. The following actions to achieve this are detailed below;
| 82% | 66.53% | Majors Triage Review | EJ/MW | Aim of reducing each patient's LOS by 10mins was agreed by the team with a lengthy time scale put in place. To identify with team any quick improvement pieces that can be implemented in the interim | 2018-08-01 | 90 days | 7% | Mini PDSAs to be shared with team to begin improvement projects | Overall reduced performance by 7.02% compared to last week
|  |  | Diagnostics Improvement | SE/GC | Staffing to be mapped against activity and identify potential gaps of investment | 2018-08-01 | 60 days | 0.1% | Data to be shared to identify main delay areas. In patient delays to be recorded going forward with new BOXI report
|  |  | GP Assessment Area | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 5% | Paper to be submitted Friday 14th
|  |  | Short Stay Observation Unit | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 0.9% | Paper to be submitted Friday 14th
|  |  | Interface Team | JS/GC | Staffing to be mapped against activity with the aim of expanding to seven days a week | 2018-08-01 | 60 days | Awaiting feedback regarding staffing and how many additional patients can be reviewed | Staffing and activity to be mapped
|  |  | Avoiding admission to main arc | JS/GC | Home First & locality involvement required along with hot clinic expansion to help quanitfy the admission avoidance numbers | 2018-09-01 | 90 days | 0.2%
|  |  | Ambulatory Care Expansion | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 2% | Paper to be submitted Friday 14th
|  |  | AMU Workforce Review | JS/GC | AHP, OT/PT, Pharmacy levels to be included | 2018-09-01 | 90 days | 0.2% | To be planned
|  |  | Flow Coordinator Role | GC/JW | Role to be reviewed along with escalation policy | 2018-09-01 | 60 days | 2% | Flow role review trial began Monday 10th
Flow Three | Improve medical admission pathways to 85%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identified below;
| 80% | 71.88% | Reducing bed occupancy in the main arc | GC |  | 2018-09-01 | 90 days | 1% |  | Overall improved performance by 1.05% compared to last week
|  |  | LOS Improvement Board | CM/MP | Follow up meetings with future directorates to be put in diaries | 2018-03-01 | 90 days | 1% | MOE/Stroke/Acute & General Medicine meetings held. Awaiting dates for rest of directorates
Flow Four | Improve surgical admission pathways to 75%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identifed below;
| 75% | 62.44% | Hot Clinic Access/Ambulatory Care | IG/KT | Team to review all hot clinic pathways and ensure parity across surgical footprint | 2018-08-01 | 60 days | 5% | Paper completed and to be submitted to A&G | Overall reduced performance by 6.88% compared to last week
|  |  | Specialty Pull | IG/MG/CM | A succint pathway to be put in place across the surgical directorate as a whole so that patients can be admitted earleir in their emergency pathway | 2018-08-01 | 90 days | 2% | Meetings ongoing with Medicine and Surgical CSM teams
Data & Recording | To align our reporting with SG and to allow us to focus and monitor improvement
|  |  | New suite of reports to track against the Flows | ADR/RP | LAS to meet to discuss future Tableau plans | Ongoing | 60 days | n/a | Robyn emailing Amanda Kirkpatrick with possibility of establishing SLWG
Adjusted Performance for September | 91% | 75% MTD

## Week 2 - WC 10th
RIE Unscheduled Care Priorities Workplan
September Week Beginning 10.09.18
Performance Trajectory submitted: 91.3%
Weekly Performance: 73.2%
| Sept Trajectory | Week's Performance | Priority | Lead | Priorities to be addressed | Anticipated Start Date | Timescales | Overall Anticipated Performance Improvement | Main Issues | Update Progress
Flow One | MI improvement in performance to achieve 96% for the month with longer term view of achieving 100%. To achieve this, the following actions need to be addressed;
| 98% | 91.58% | NHS 24 Redirection | GC | Longer term plan to be discussed following Festival trial | 2018-08-01 | 60 days | 0.001% | Follow up meetng to be held to confirm long term redirection options | Overall improved performance by 3.13% compared to last week
|  |  | Demand & Capacity | SB | Daily Flow ANP consistency to be put in place. Now looking at what can be done to improve TC4 patients | 2018-09-01 | 30 days | 0.2% | Main breach reason related to first assessment. Lead ANP following up with team regularly to reduce this delay which is mainly during the out of hours period
|  |  | Dedicated MIU | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 4% | Paper to be presented at 4EAS Board this week
Flow Two | Improve first assessment within majors to 85%. The following actions to achieve this are detailed below;
| 82% | 59.66% | Majors Triage Review | EJ/MW | Aim of reducing each patient's LOS by 10mins was agreed by the team with a lengthy time scale put in place. To identify with team any quick improvement pieces that can be implemented in the interim | 2018-08-01 | 90 days | 7% | Triage PDSA was to trial on Thursday but was cancelled due to staffing levels. To be reviewed this week. | Overall reduced performance by 6.87% compared to last week
|  |  | Diagnostics Improvement | SE/GC | Staffing to be mapped against activity and identify potential gaps of investment | 2018-08-01 | 60 days | 0.1% | Data to be shared to identify main delay areas. In patient delays to be recorded going forward with new BOXI report
|  |  | GP Assessment Area | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 5% | Paper to be presented at 4EAS Board this week
|  |  | Short Stay Observation Unit | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 0.9% | Paper to be presented at 4EAS Board this week
|  |  | Interface Team | JS/GC | Staffing to be mapped against activity with the aim of expanding to seven days a week | 2018-08-01 | 60 days | Awaiting feedback regarding staffing and how many additional patients can be reviewed | To be mapped
|  |  | Avoiding admission to main arc | JS/GC | Home First & locality involvement required along with hot clinic expansion to help quanitfy the admission avoidance numbers | 2018-09-01 | 90 days | 0.2% | Admission avoidance data to be collated from these services
|  |  | Ambulatory Care Expansion | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 2% | Paper to be presented at 4EAS Board this week
|  |  | AMU Workforce Review | JS/GC | AHP, OT/PT, Pharmacy levels to be included | 2018-09-01 | 90 days | 0.2% | To be planned
|  |  | Flow Coordinator Role | GC/JW | Role to be reviewed along with escalation policy | 2018-09-01 | 60 days | 2% | Trial still ongoing. No data to present today as bank holiday but will feedback for next week
Flow Three | Improve medical admission pathways to 85%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identified below;
| 80% | 68.18% | Reducing bed occupancy in the main arc | GC |  | 2018-09-01 | 90 days | 1% |  | Overall reduced performance by 3.70% compared to last week
|  |  | LOS Improvement Board | CM/MP | Follow up meetings with future directorates to be put in diaries | 2018-03-01 | 90 days | 1% | GI/Renal/TP and CTR to meet with Board this month. Ongoing work with Gen Med and MOE
Flow Four | Improve surgical admission pathways to 75%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identifed below;
| 75% | 58.56% | Hot Clinic Access/Ambulatory Care | IG/KT | Team to review all hot clinic pathways and ensure parity across surgical footprint | 2018-08-01 | 60 days | 5% | Paper completed and to be submitted to enable additional pathways | Overall reduced performance by 3.88% compared to last week
|  |  | Specialty Pull | IG/MG/CM | A succint pathway to be put in place across the surgical directorate as a whole so that patients can be admitted earleir in their emergency pathway | 2018-08-01 | 90 days | 2% | Meetings ongoing with medicine and surgical CSM teams
Data & Recording | To align our reporting with SG and to allow us to focus and monitor improvement
|  |  | New suite of reports to track against the Flows | ADR/RP | LAS to meet to discuss future Tableau plans | Ongoing | 60 days | n/a | New BOXI report created which provides breach breakdown within each flow
Adjusted Performance for September | 91% | 74.1% MTD

## Week 3 - WC 17th
RIE Unscheduled Care Priorities Workplan
September Week Beginning 17.09.18
Performance Trajectory submitted: 91.3%
Weekly Performance: 72.5%
| Sept Trajectory | Week's Performance | Priority | Lead | Priorities to be addressed | Anticipated Start Date | Timescales | Overall Anticipated Performance Improvement | Main Issues | Update Progress
Flow One | MI improvement in performance to achieve 96% for the month with longer term view of achieving 100%. To achieve this, the following actions need to be addressed;
| 98% | 93.3% | NHS 24 Redirection | GC | Longer term plan to be discussed following Festival trial | 2018-08-01 | 60 days | 0.001% | Follow up meetng to be held to confirm long term redirection options | Overall improved performance by 1.72% compared to last week
|  |  | Demand & Capacity | SB | Daily Flow ANP consistency to be put in place. Now looking at what can be done to improve TC4 patients | 2018-09-01 | 30 days | 0.2% | 100% compliance noted for consecutve days in TC7 flow. Work ongoing to include TC4 patients
|  |  | Dedicated MIU | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 4% | Awaiting feedback from 4EAS Board
Flow Two | Improve first assessment within majors to 85%. The following actions to achieve this are detailed below;
| 82% | 60.63% | Majors Triage Review | EJ/MW | Aim of reducing each patient's LOS by 10mins was agreed by the team with a lengthy time scale put in place. To identify with team any quick improvement pieces that can be implemented in the interim | 2018-08-01 | 90 days | 7% | Triage PDSA to be carried out next week | Overall improved performance by 0.97% compared to last week
|  |  | Diagnostics Improvement | SE/GC | Staffing to be mapped against activity and identify potential gaps of investment | 2018-08-01 | 60 days | 0.1% | Data to be shared to identify main delay areas. In patient delays BI report created. To be reviewed and shared with wider team
|  |  | GP Assessment Area | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 5% | Awaiting feedback from 4EAS Board
|  |  | Short Stay Observation Unit | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 0.9% | Awaiting feedback from 4EAS Board
|  |  | Interface Team | JS/GC | Staffing to be mapped against activity with the aim of expanding to seven days a week | 2018-08-01 | 60 days | Awaiting feedback regarding staffing and how many additional patients can be reviewed | To be mapped
|  |  | Avoiding admission to main arc | JS/GC | Home First & locality involvement required along with hot clinic expansion to help quanitfy the admission avoidance numbers | 2018-09-01 | 90 days | 0.2% | Admission avoidance data to be collated from these services
|  |  | Ambulatory Care Expansion | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 2% | Awaiting feedback from 4EAS Board Papers to go to A&G next Tuesday
|  |  | AMU Workforce Review | JS/GC | AHP, OT/PT, Pharmacy levels to be included | 2018-09-01 | 90 days | 0.2% | To be confirmed
|  |  | Flow Coordinator Role | GC/JW | Role to be reviewed along with escalation policy | 2018-09-01 | 60 days | 2% | Trial still ongoing with escalation charts to be reviewed this week
Flow Three | Improve medical admission pathways to 85%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identified below;
| 80% | 62.96% | Reducing bed occupancy in the main arc | GC |  | 2018-09-01 | 90 days | 1% |  | Overall reduced performance by 5.22% compared to last week
|  |  | LOS Improvement Board | CM/MP | Follow up meetings with future directorates to be put in diaries | 2018-03-01 | 90 days | 1% | GI/Renal/TP and CTR to meet with Board this month. Ongoing work with Gen Med and MOE
Flow Four | Improve surgical admission pathways to 75%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identifed below;
| 75% | 58.22% | Hot Clinic Access/Ambulatory Care | IG/KT | Team to review all hot clinic pathways and ensure parity across surgical footprint | 2018-08-01 | 60 days | 5% | Papers to go to A&G next Tuesday | Overall reduced performance by 0.34% compared to last week
|  |  | Specialty Pull | IG/MG/CM | A succint pathway to be put in place across the surgical directorate as a whole so that patients can be admitted earleir in their emergency pathway | 2018-08-01 | 90 days | 2%
Data & Recording | To align our reporting with SG and to allow us to focus and monitor improvement
|  |  | New suite of reports to track against the Flows | ADR/RP | LAS to meet to discuss future Tableau plans | Ongoing | 60 days | n/a | New daily automated reports created and to be shared with team from this week
Adjusted Performance for September | 91% | 73.6% MTD

## Week 4 - WC 24th
RIE Unscheduled Care Priorities Workplan
September Week Beginning 24.09.18
Performance Trajectory submitted: 91.3%
Weekly Performance:
| Sept Trajectory | Week's Performance | Priority | Lead | Priorities to be addressed | Anticipated Start Date | Timescales | Overall Anticipated Performance Improvement | Main Issues | Update Progress
Flow One | MI improvement in performance to achieve 96% for the month with longer term view of achieving 100%. To achieve this, the following actions need to be addressed;
| 98% |  | NHS 24 Redirection | GC | Longer term plan to be discussed following Festival trial | 2018-08-01 | 60 days | 0.001%
|  |  | Demand & Capacity | SB | Daily Flow ANP consistency to be put in place. Now looking at what can be done to improve TC4 patients | 2018-09-01 | 30 days | 0.2%
|  |  | Dedicated MIU | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 4%
Flow Two | Improve first assessment within majors to 85%. The following actions to achieve this are detailed below;
| 82% |  | Majors Triage Review | EJ/MW | Aim of reducing each patient's LOS by 10mins was agreed by the team with a lengthy time scale put in place. To identify with team any quick improvement pieces that can be implemented in the interim | 2018-08-01 | 90 days | 7%
|  |  | Diagnostics Improvement | SE/GC | Staffing to be mapped against activity and identify potential gaps of investment | 2018-08-01 | 60 days | 0.1%
|  |  | GP Assessment Area | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 5%
|  |  | Short Stay Observation Unit | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 0.9%
|  |  | Interface Team | JS/GC | Staffing to be mapped against activity with the aim of expanding to seven days a week | 2018-08-01 | 60 days | Awaiting feedback regarding staffing and how many additional patients can be reviewed
|  |  | Avoiding admission to main arc | JS/GC | Home First & locality involvement required along with hot clinic expansion to help quanitfy the admission avoidance numbers | 2018-09-01 | 90 days | 0.2%
|  |  | Ambulatory Care Expansion | Scoping | As part of Scoping Team - Paper for submission mid Sept | 2018-09-01 | 90 days | 2%
|  |  | AMU Workforce Review | JS/GC | AHP, OT/PT, Pharmacy levels to be included | 2018-09-01 | 90 days | 0.2%
|  |  | Flow Coordinator Role | GC/JW | Role to be reviewed along with escalation policy | 2018-09-01 | 60 days | 2%
Flow Three | Improve medical admission pathways to 85%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identified below;
| 80% |  | Reducing bed occupancy in the main arc | GC |  | 2018-09-01 | 90 days | 1%
|  |  | LOS Improvement Board | CM/MP | Follow up meetings with future directorates to be put in diaries | 2018-03-01 | 90 days | 1%
Flow Four | Improve surgical admission pathways to 75%. To achieve this, this will include the previously identified actions in Flow 2 in conjunction with actions identifed below;
| 75% |  | Hot Clinic Access/Ambulatory Care | IG/KT | Team to review all hot clinic pathways and ensure parity across surgical footprint | 2018-08-01 | 60 days | 5%
|  |  | Specialty Pull | IG/MG/CM | A succint pathway to be put in place across the surgical directorate as a whole so that patients can be admitted earleir in their emergency pathway | 2018-08-01 | 90 days | 2%
Data & Recording | To align our reporting with SG and to allow us to focus and monitor improvement
|  |  | New suite of reports to track against the Flows | ADR/RP | LAS to meet to discuss future Tableau plans | Ongoing | 60 days | n/a
Adjusted Performance for September | 91%

## ISD Scotland Flow Definitions
ISD SCOTLAND DEFINITIONS FOR ED FLOW CATEGORIES
Flow 1 - Minor Injury and Illness, including care provided in A&E Departments, in Minor Injury Units and through schemes such as Paramedic See and Treat.
Flow 2 - Acute Assessment, this includes the 'majors patients' in A&E and patients referred to Acute Assessment and Receiving Units. The key to understanding the definition of this flow is the patients' predominant need for ongoing assessment to determine the next step in their care pathways (it is accepted that it may not be known how long a patient will remain in the Assessment Area/AMU and that this flow is recorded upon discharge from A&E and is not updated upon discharge/transfer from the AMU). This flow should be limited to a maximum of 48-72 hours in Assessment Units reflecting patient needs. However, the 4-hour waiting time standard applies to trolleyed/chair areas in these units, to ensure that patients are treated equitably irrespective of the point of access and in the most appropriate clinical environment.
Flow 3 - Medical Admissions, patients who require a period of acute hospital care under the management of a Medical or Elderly Care team. Work in this flow will be linked to the chronic disease management agenda.
Flow 4 - Surgical Admissions, patients who require a period of acute hospital care, under the management of a Surgical Team. Work in this flow will be linked to redesign of the elective surgical flow and links to theatres' redesign.
Flow 5 - Out-of-Hospital Care, this flow will support the development of alternatives to hospital attendance and admission, reducing waits and delays for patients who need urgent hospital assessment and treatment, and facilitating timely discharge for those who are ready for discharge from hospital. Involvement of partners in community care will be essential to delivery of significant change.

## Sheet1
August
Trajectory |  | Performance
Flow 1 | 98% | Flow 1
Flow 2 | 82% | Flow 2
Flow 3 | 80% | Flow 3
Flow 4 | 75% | Flow 4